## WP Other Costs Reporting
| Work Package Number | C11426_PRJ-7460.04 EAP3.0 |  | fill in blue cells |  |  | Booked
| Work Package Leader: | Pietro Serra |  |  |  |  | Forecast
| Reporting Period (Month) | 2019-11 and 12 forecast
LC1 | Other ABB manpower cost
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
| CZ OPC | To be defined | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LC2 | External manpower cost
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
| Gruppo Sigla | SCADA BESS (A. Zucca) | 0 | 0 | 0 | 0 | 3918.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3918.75
| ELETEC | Template project review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512 | 0 | 0 | 1512
| Industrial Solutions | e-mesh SCADA licensing tool SW dev. Support (order 4400065711) | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4895
| EDV | PPC rendering (order 4400068361) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 0 | 4895 | 3918.75 | 0 | 0 | 0 | 0 | 1512 | 0 | 1500 | 11825.75
OC1 | Internal lab cost
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
| OPAL-RT | 1 core activation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC2 | External lab cost
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC3 | University cost
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC4 | Material, tools and prototyping
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
| CO.EL.ME. | Training rack and kit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DE-2877 | RTU500 Material for laboratory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CO.EL.ME. | Testing rack adaptation cost (order 4400064595/E2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ABB EL | REF615 ANSI for 2030.7 and .8 testing (order 4400068280) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6380 | 6380
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6380 | 6380 | 6380
OC5 | Travel
| Supplier | Description | JAN | FEB | MRZ | APR | MAI | JUN | JUL | AUG | SEP | OKT | NOV | DEZ | Total
|  | Project travels | 0 | 0 | 242 | 567.44 | 107.9 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 1093.34
|  | Project support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (in local Currency - EURO) |  | 0 | 0 | 242 | 567.44 | 107.9 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 1093.34
| Total (enter name of local Currency) - EURO |  | 0 | 0 | 242 | 5462.44 | 4026.65 | 176 | 0 | 0 | 0 | 1512 | 0 | 7880 | 19299.09 | Euro
|  |  | 0 | 0 | 283.14 | 6391.0548 | 4711.1805 | 205.92 | 0 | 0 | 0 | 1769.04 | 0 | 9219.6 | 22579.9353 | $ | 1.1728
|  |  | 0 | 0 | 0.28314 | 6.3911 | 4.7112 | 0.20592 | 0 | 0 | 0 | 1.769 | 0 | 9.2196 | 22.5799 | k$
Note on A6: Labour cost
Note on M8: Setup with CZ-OPC not finalized
Note on N8: Setup with CZ-OPC not finalized
Note on O8: Setup with CZ-OPC not finalized
Note on A24: Outlay Cost
Note on M26: Initially foresees as a 25k cost item
Note on G62: MTU P. Serra
Note on N62: M. Filippone 2 weeks testing in US 2019.10.12 on BESS project, training on EAP
Note on R70: Conversion rate To be updated yearly according to NORRD ratings

## WP forecast
[8 empty] | 1608 | Hours/year | [21 empty] | 1760
[8 empty] | 66.17 | FTE rate €/h | [10 empty] | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 20 | 20 | 20 | 15
[8 empty] | NORRD BUDGET | [11 empty] | FROM NORRD REPORTS
PROGETTO SAP | APERTURA SAP | WP NORRD | LINEA NORRD | TITLE | PL | PM | NOTES | FTE [hours] | Cost Man Years. R&D FTE [€] | Other ABB man power cost [€] | External man power cost [€] | Internal lab cost [€] | External lab cost [€] | University cost [€] | Material tools and prototyping [€] | Travel cost [€] | Total [€] | STATO |  | H. 06.01 | H. 06.02 | H. 06.03 | H. 06.04 | H. 06.05 | H. 06.06 | H. 06.07 | H. 06.08 | H. 06.09 | H. 06.10 | H. 06.11 | H. 06.12 | H. TOT
C11424 | 2019-01-29 | WP-xxxx.nn | 2884.2 | AAP3.0 | P. Serra | F. Vercellotti | AAP - 1st release 2019 | 2814 | 186202.38 | 0 | 15000 | 0 | 0 | 0 | 10000 | 5000 | 216202.38 |  |  | 320 | 320 | 847 | 482 | 597 | 565 | 510 | 254 | 405 | 579 | 428 | 100 | 5407 | 32736
[8 empty] | 1.302% | 86.12%
[8 empty] | 2814 | 186202.38 | [6 empty] | 5000 | 216202.38 |  | Total actual | 320 | 640 | 1487 | 1969 | 2566 | 3131 | 3641 | 3895 | 4300 | 4879 | 5307 | 5407 | 5407
[20 empty] | FROM NORRD REPORTS H. 06.01: NORRD REPORT; FROM NORRD REPORTS H. 06.12: Total hours forecast | 357781.19 | 419622.3642
[20 empty] | FROM NORRD REPORTS H. 06.01: FORECAST; FROM NORRD REPORTS H. 06.12: Total cost forecast | 19299.09 | 22634.8673
[20 empty] | FROM NORRD REPORTS H. 06.12: Total WP forecast | 377080.28 | 442257.2316
-80.28
[20 empty] | FROM NORRD REPORTS H. 06.01: Note on forecast | -1.2132
- 20k€ shall be moved on cost center as investment for OPC consultancy
Note on I5: Resources 100% P. Serra 100% M. Filippone 100% M. Calì 50% S. Picerno
Note on Y5: PS,MF,SP,MC
Note on Z5: PS,MF,SP,MC